## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish a plant delivery and logistics plan | 1.1 | source materials for packaging | Fulfillment Director |  | sources materials
| 1.2 | hire delivery drivers | Human Resources Specialist |  | oversees hiring
| 1.3 | calculating the delivery fees | Financial Analyst |  | tracks costs and revenue
Select and install supply chain software and equipment | 2.1 | supervise vendor setup of inventory management and fulfillment software | Inventory Manager |  | ensures software is installed and set up properly
| 2.2 | supervise vendor installation of fulfillment equipment | Fulfillment Director |  | ensures equipment is functional with the help of the Quality Assurance Tester
| 2.3 | determine internal safety protocols for the equipment | Quality Assurance Tester |  | determines safety protocols and best practices
Develop and launch an employee training program | 3.1 | develop training sessions | Human Resources Specialist |  | develops the training sessions with the help of the Training Manager
| 3.2 | train employees to use the software and equipment | Training Manager |  | runs the training program on the established protocols
| 3.3 | monitor employee progress and improve training processes | Training Manager |  | refines the training process